## Risk Register
| Project: APWA Self-Assessment | [5 empty] | KEY:
Key/ Critical
Intermediate
Minor
RISK IDENTIFICATION & MITIGATION | [9 empty] | ACTION PLAN |  |  |  | COMMENTS
Ref | Category | Risk | Potential Impact | Completed Mitigation Action (to date) | Probability | Impact | Risk Score/ Category | Cost Impact (Project Costs) | Schedule Impact [weeks] | Action Plan | Responsible | Next Action Target Date | Date Achieved
1 | External | Public does not approve staff's submittal at Council Meeting | Could delay entire accreditation process; could result in expanded scope as directed by Council (add new services) |  | 4 | 3 | 12
2 | Internal | City Council delays approval to submit self-assessment | Self-assessment project delayed as is overall accreditation process |  | 2 | 3 | 6
3 | Internal | Steering Committee does not sign off on pursuing rest of accreditation process | Department does not achieve long term objective of accreditation |  | 5 | 4 | 20
4 | Internal | City leadership changes and accreditation is no longer an organizational priority | Invested resources to pursue the project are wasted; costs of accreditation are lost; organization does not gain credibility through accreditation |  | 3 | 3 | 9
5 | Internal | City leadership changes meeting date due to scheduling conflicts with other agenda items | Self-assessment project delayed as is overall accreditation process |  | 2 | 3 | 6
6 | Internal | Inaccurate assumptions during the planning phase | Agreed strategies and plans in scope of work requires additional review and amendment; cost and time implications |  | 2 | 4 | 8
7 | Internal | Employees are unable to attend the Public Works Employee Kickoff Meeting | Employees will not understand the importance of the self-assessment process and fully support the effort |  | 3 | 2 | 6
8 | Internal | Stakeholders are unable to attend the Stakeholder Kickoff Meeting | Stakeholders will not understand the importance of the self-assessment process and fully support the effort |  | 3 | 2 | 6
9 | Internal | Employees do not fully support the self-assessment process | The process will be much more difficult, signficantly more challenging and will take longer to accomplish |  | 3 | 2 | 6
10 | External | An outside qualified consultant is not obtained | A gap analysis with recommendations for correcting deficiencies is not conducted |  | 3 | 3 | 9
11 | Client | APWA training workshop is ineffective | An plan for training personnel is not developed; documentation preparation is ineffective |  | 1 | 2 | 2
12 | External | Consultant exceeds budgeted time & cost due to Self-Assessment taking longer then expected | May have to go to Council for additional funding, or internal staff may have to pick up more work that the consultant would have done. |  | 2 | 4 | 8
13 | Internal | Data received from consultant is incomplete or is substandard | Consultant would have to redo work which would impact the project schedule. May result in legal action if consultant resists. |  | 2 | 4 | 8
14 | Internal | Another higher priority project takes away available resources | The project would be delayed until resources become available, the result impacts the overall project schedule. |  | 5 | 4 | 20
15 | External | APWA Self-Assessment software develops a bug found during QA/QC and data needs to be re-entered | This would impact available resources, project schedule, and project cost. |  | 2 | 3 | 6
16 | External | Consultant delivers data ahead of time and under budget | This would result in extra cushion in both the project budget and schedule |  | 1 | 3 | 3
17 | Internal | Sign-off by steering committee leads to additional work requirements | Possible redesign and additional requirements are added to project creating delays in kick-off |  | 1 | 4 | 4
18 | External | No qualifying bids are accepted for the consultant Professional Services Agreement | Additional resources are required due when staff is already stretched to capacity creating OT and increading budget and possibly schedule OR sponsor determines it needs to be re-bid |  | 4 | 5 | 20
19 | Internal | Sponsor elects to reduce the number of practices in each chapter to be included in self-assessment | Possible reduction in schedule due to less practices being submitted |  | 2 | 5 | 10
20 | Internal | Inaccurate assumptions during the planning phase | Assumptions in estimating resources, schedule, budget, stakeholders and/or communication haven't been fully identified creating changes to several plans |  | 2 | 5 | 10
21 | Organizational | Resource conflicts with other projects | Not enough resources are available or outside departments don't provide the resources necessary to stay within schedule |  | 4 | 4 | 16
22 | External | Bids for consultant come in lower than expected | Budget is less than estimated saving funds for the project |  | 2 | 5 | 10
23 | Organizational | Approval and decision processes cause delays | Sponsor and/or Steering Committee aren't available for meetings that are scheduled for approvals causing delays |  | 4 | 5 | 20
24 | Internal | Electronic holding file compromised; files accidentally erased or corrupted and not recoverable | Significant rework and addition of time |  | 2 | 5 | 10
25 | Internal | Consultant identified none or very few gaps in data | Collapse in schedule |  | 2 | 1 | 2
26 | Internal | Consultant identifies significant gaps that cannot be addressed within the project schedule | Staff may need to reevaluate practices for submittal. Project team will need to execute contingency plans |  | 3 | 3 | 9
27 | External | APWA software unstable/unreliable | Delays in uploading data. May define/limit which users will have the ability to upload data to the system. |  | 3 | 2 | 6
28 | Internal | New policies/procedures take too long to develop, or team is unable to gain consensus on new policies/procedures | Adds time to schedule. |  | 3 | 2 | 6
29 | External | APWA unable to make site visit during time frame necessary | Re-evaluate schedule. |  | 2 | 2 | 4
30 | Internal | Data not available in electronic format | Additional resources needed to digitize data, will add time to schedule |  | 4 | 2 | 8
31 | [6 empty] | 0
32 | [6 empty] | 0
33 | [6 empty] | 0
34 | [6 empty] | 0
35 | [6 empty] | 0
36 | [6 empty] | 0
37 | [6 empty] | 0
38 | [6 empty] | 0
39 | [6 empty] | 0
40 | [6 empty] | 0
41 | [6 empty] | 0
42 | [6 empty] | 0
43 | [6 empty] | 0
44 | [6 empty] | 0
45 | [6 empty] | 0
46 | [6 empty] | 0
47 | [6 empty] | 0
48 | [6 empty] | 0
49 | [6 empty] | 0
50 | [6 empty] | 0
51 | [6 empty] | 0
52 | [6 empty] | 0
53 | [6 empty] | 0
54 | [6 empty] | 0
55 | [6 empty] | 0
56 | [6 empty] | 0
57 | [6 empty] | 0
58 | [6 empty] | 0
59 | [6 empty] | 0
60 | [6 empty] | 0
61 | [6 empty] | 0

## Risk Events Defined (hidden)
Organizational
Project Management
Design
Marketing / Communication
Construction
Quality Standards
Environmental/Regulatory
External
Community
Handover

## Risk Scoring
Risk Scoring Matrix | [7 empty] | Probability Categories
Impact | Very High/ Critical | 5 |  | 4 |  | 2 |  | Description |  | Prob | Scale Value
| High/ Critical | 4 | 1 | 3 |  | 1 | 2 | VH | Imminent | > 95% | 5
| Medium/ Serious | 3 | 1 | 3 | 3 | 1 |  | H | Probable | 71-94% | 4
| Low/ Marginal | 2 | 1 | 1 | 5 | 1 |  | M | Could happen | 30-70% | 3
| Very Low/ Marginal | 1 |  | 1 |  |  |  | L | Improbable | 5-29% | 2
|  |  | 1 | 2 | 3 | 4 | 5 | VL | Highly unlikely | <5% | 1
|  |  | Very Low/ Improbable | Low/ Improbable | Medium/ Could happen | High/ Probable | Very High/ Probable | Impact Categories
[8 empty] | Description |  | Guide Scenario |  | Scale Value
[8 empty] | VH | Critical | Failure that involves significant rework, modification or reassessment |  | 5
[8 empty] | H | Critical | Failure that involves significant rework, modification or reassessment |  | 4
[8 empty] | M | Serious | Failure or setback that causes additional work and reassessment but containable |  | 3
[8 empty] | L | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 2
|  |  | Probability |  |  |  |  | VL | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 1
Risk Category & Action
Key/ Critical Risks - closely monitor, manage & develop fallback plans
Intermediate Risks - monitor and manage to mitigate/ include specific risk allowances in cost estimate & schedule
Minor Risks - general allowance in base cost estimate & schedule