## Resource Plan
1. Initiate | [42 empty] | THANKSGIVING |  |  |  | CHRISTMAS | NEW YEAR
2. Plan
3. Project Kick-Off
4. Execution
5. Monitoring
6. Close Out
| Q1 2015 | [8 empty] | Q2 2015 | [12 empty] | Q3 2015 | [12 empty] | Q4 2015 | [12 empty] | Q1 2016 | [12 empty] | Q2 2016 | [11 empty] | Q3 2016
Project Deliverables | Business Case, Project Charter, Steering Committee | [6 empty] | Project Management Plan, Project Documents & Templates |  |  |  |  | Updated PM documents, Consultant Contract, Kick-off Meetings & Materials, Formal APWA Application submittals | [12 empty] | Data Collection, Gap Analysis Report, Quality Project Documents, Data Input into Software | [37 empty] | Council Meeting, Stakeholder Meeting, Closeout Celebrations, Next Phase Project Business Case & Charter
Timeline | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28 | 2015-01-04 | 2015-01-11 | 2015-01-18 | 2015-01-25 | 2015-02-01 | 2015-02-08 | 2015-02-15 | 2015-02-22 | 29-Feb | 2015-03-07 | 2015-03-14 | 2015-03-21 | 2015-03-28 | 2015-04-04 | 2015-04-11 | 2015-04-18 | 2015-04-25 | 2015-05-02 | 2015-05-09 | 2015-05-16 | 2015-05-23 | 2015-05-30 | 2015-06-06 | 2015-06-13 | 2015-06-20 | 2015-06-27 | 2015-07-04 | 2015-07-11 | 2015-07-18 | 2015-07-25 | 2015-08-01 | 2015-08-08 | 2015-08-15 | 2015-08-22 | 2015-08-29
Core Project Team
Project Manager- Craddock Stropes |  |  | 2 | 5 | 1 | 1 | 6 | 6 | 30 | 2 | 6 | 8 | 4 | 8 | 2 | 1 | 1 | 4 |  | 3 | 1 | 8 | 8 | 12 | 24 | 28 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 24 | 24 | 16 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 8 | 10 | 12 | 12 | 10 | 13 | 2 | 2 | 2 | 1 | 1 | 4 |  | 1 |  |  | 1 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1
Project Consultant | [16 empty] | 1 | 2 |  | 1 |  |  | 2 | 10 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 25 | 24 |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 | [10 empty] | 2 | 2 |  | 1 |  |  | 1 | 732
Senior Management Analyst-Bonnie Elliott |  |  |  | 2 | 1 |  | 5 | 5 | 20 | 1 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 |  | 1 |  |  | 2 |  | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 14 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 1 | [5 empty] | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1
Business System Specialist- Greg MacLellan |  |  |  | 2 | 1 |  | 6 | 5 | 20 | 1 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 |  | 1 |  |  | 2 |  | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 24 | 16 | 16 | 18 | 18 | 18 | 18 | 22 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1
Management Analyst-Christie Marcella |  |  |  | 2 | 2 |  | 5 | 5 | 20 | 1 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 |  | 1 |  |  | 2 |  | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 14 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 1 | [5 empty] | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1
Management Analyst-Jennifer Marinov |  |  |  | 2 | 1 |  | 6 | 5 | 20 | 1 | 2 | 2 | 2 | 2 | 2 |  | 1 | 2 |  | 1 |  |  | 2 |  | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 14 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 1 | [5 empty] | 1 |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1
Leadership
Project Sponsor-Pat Thomas |  |  | 2 | 3 |  | 1 | 2 | 4 | 10 | 1 | 1 | 1 | 3 | 2 | [5 empty] | 5 |  | 3 | 2 | 1 | 8 | 4 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 4 | 4 | [22 empty] | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 2 | 1 |  |  |  |  | 1
Steering Committee-Gary Barberio | [5 empty] | 1 | [5 empty] | 1 | [53 empty] | 1 | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 1
Steering Committee- Joe Garuba | [5 empty] | 1 |  |  |  | 1 |  | 1 | [5 empty] | 2 |  | 5 |  | 3 | 1 |  | 4 | 4 | 4 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  |  | 2 | [20 empty] | 1 | [11 empty] | 1 |  |  |  |  | 1
Steering Committee- Ed Garbo | [5 empty] | 1 |  |  |  | 1 |  | 1 | [53 empty] | 1 | [6 empty] | 2 |  |  |  |  | 1 |  |  |  |  | 1
Steering Committee- Ron Kemp | [5 empty] | 1 |  |  |  | 1 |  | 1 | [11 empty] | 1 | [41 empty] | 1 | [6 empty] | 2 |  |  |  | 1 | 1 |  |  |  |  | 1
City Council | [82 empty] | 1
Steve Sarkozy | [72 empty] | 1 | [9 empty] | 1
Other City Resources
Utilities Director-Wendy Chambers | [8 empty] | 1 | 1 |  |  |  | 1 |  |  |  | 2 |  | 5 |  | 3 | 1 |  | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Streets Manager-John Maashoff | [8 empty] | 1 | 1 |  |  |  | 1 |  |  |  | 2 | [6 empty] | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Finance Director- Kevin Branca | [44 empty] | 1 | [27 empty] | 1 |  |  |  | 1 | [5 empty] | 1
I.T. Director- Tina Steffan | [72 empty] | 1 | [9 empty] | 1
H.R. Manager- Cheri Abbott | [12 empty] | 1 | 1 | [58 empty] | 1 | [9 empty] | 1
Emergency Preparedness Mgr-David Harrison | [72 empty] | 1 | [9 empty] | 1
Communications Mgr-Kristina Ray | [69 empty] | 1 | [12 empty] | 1
CED Director-Glen Van Peski | [8 empty] | 1 | 1 |  |  | 1 | 1 | [5 empty] | 5 |  | 3 | 1 |  | 4 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 2 | 4 | 2 | 2 | 2 | 4 | 2 | 2 | [42 empty] | 1
Finance Mgr-Colette Wengenroth | [13 empty] | 1 | [9 empty] | 1 | [20 empty] | 1 | [37 empty] | 1
Traffic Engineer- Doug Bilse | [8 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  | 2 | [6 empty] | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Senior Engineer-Marshal Plantz | [8 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  | 2 | [6 empty] | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Environmental Mgr-Elaine Lukey | [8 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  | 2 | [6 empty] | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Engineering Mgr-Patrick Vaughn | [8 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  | 2 | [6 empty] | 8 | 4 | 4 | 8 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 | 4 | 8 | 4 | 4 |  |  |  |  | 2 | [37 empty] | 1
Management Analyst-Fred Gaines Jr. | [8 empty] | 1 | 1 |  |  | 1 | 1 |  |  |  | 2 | [6 empty] | 6 | 6 | 6 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  |  | 2 | [11 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [20 empty] | 1
Management Analyst-Steve Hodges | [8 empty] | 1 | 1 |  |  | 1 | 1 | [10 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [42 empty] | 1
Program Mgr- Lolly Sangster | [12 empty] | 1 | 1 | [10 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [42 empty] | 1
Management Analyst-Ligeia Heagy | [8 empty] | 1 | 1 |  |  | 1 | 1 | [10 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [42 empty] | 1
Engineering Mgr-Kristen Plonka | [12 empty] | 1 | 1 | [10 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [42 empty] | 1
Utilities Manager- Don Wasko | [12 empty] | 1 | 1 | [10 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [42 empty] | 1
Utilities Manger- Angel Quintero | [12 empty] | 1 | 1 | [10 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [42 empty] | 1
Business System Specialist- Stephanie Harrison | [13 empty] | 1 | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [16 empty] | 8 | 8 | 8 | 8 | 8 | 8 | [20 empty] | 1 | 210
Business System Specialist- Tye Gillespie | [13 empty] | 1 | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [16 empty] | 8 | 8 | 8 | 8 | 8 | 8 | [20 empty] | 1 | 210
Public Works Admin- Shelby Nelson | [12 empty] | 1 | 3 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [16 empty] | 8 | 8 | 8 | 8 | 8 | 8 | [20 empty] | 1 | 309
Public Works Admin- Janean Hawney | [12 empty] | 1 | 3 | [10 empty] | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 24 | 24 | 24 | [16 empty] | 8 | 8 | 8 | 8 | 8 | 8 | [20 empty] | 1 | 365
Public Works Admin- Dale Willis | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Shea Sainz | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Kim Stankavich | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Pat Wise | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Gail Jones | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Marcia Long | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Public Works Admin- Serena Schlosser | [13 empty] | 1 | [10 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [42 empty] | 1 | 258
Totals | 0 | 0 | 4 | 16 | 6 | 6 | 30 | 30 | 130 | 20 | 15 | 21 | 30 | 49 | 10 | 1 | 6 | 30 | 0 | 28 | 1 | 20 | 23 | 25 | 386 | 352 | 348 | 368 | 320 | 350 | 320 | 312 | 312 | 346 | 320 | 320 | 320 | 374 | 342 | 342 | 96 | 96 |  | 96 | 130 | 96 |  |  | 96 | 96 | 96 | 96 | 96 | 96 | 97 | 96 | 48 | 50 | 56 | 52 | 50 | 53 | 4 | 3 | 7 | 7 | 5 | 4 | 0 | 7 | 0 | 0 | 16 | 1 | 1 | 5 | 21 | 12 | 1 | 6 | 1 | 1 | 44 | 7671
[85 empty] | City labor hrs | 6939
[85 empty] | Non mgmt hrs | 2900