## WBS
WORK BREAKDOWN STRUCTURE SEQUENCE
Project Title: APWA Self-Assessment
Date Prepared: 04/1/2015
TASK | DESCRIPTION OF TASK | ACCEPTANCE CRITERIA | WORK PRODUCTS | RESOURCES | EFFORT | DURATION | PREDECESSORS
[5 empty] | E(hours) | D(Weeks) | Predecessor
1. Initiate |  |  |  |  | 32 | 4
1.1. Establish Business Case | Project Manager develops business case to present to sponsor for approval to start project planning | Business Plan is signed of by sponsor for proceeding with project planning | Project description and desired outcome | Project Manager Project Sponsor | 4 | 1
1.2. Project Charter | Project Manager establishes project team and works together to develop project charter for presentation to steering committee to begin planning project | Project Charter is signed off by sponsor | Project Charter Draft Signed | Project Manager Project Team (4) Project Sponsor | 16 | 1 | 1.1
1.3. Initiation Gate with Steering Committee | PowerPoint presentation to Steering Committee for approval | Steering Committee gives the 'go ahead' for continuing project | Initiation Gate PowerPoint Presentation Final Signed Project Charter | Project Manager Steering Committee (3) Project Sponsor | 12 | 2 | 1.2
2. Plan |  |  |  |  | 234 | 6
2.1. Project Management Plan & Subsidiary Plans | Project Manager and Project Team work together to create Project Management Plan; identification of stakeholders and analysis for establishing communications methods; integration management plan and how to handle/validate changes to charter and other plans/work; identify risks and methods for handling; identify resources and subject matter experts, develop project requirements (SOW); quality controls and standards are developed | Sponsor approves methologies and plans identified and developed | Project Management Plan Integration Management Plan Stakeholder Management Plan Communications Management Plan Human Resources Management Plan Risk Management Plan Change Management Plan & Template | Project Manager Project Team (4) Project Sponsor | 60 | 2 | 1.3
2.2. Project Scope | Project Scope is developed outlining what is in/out of project; identify and develop requirements for project objectives | Sponsor approves methologies and scope developed | WBS & associated WBS Dictionary | Project Manager Project Team (4) Project Sponsor | 10 | 1 | 2.1
2.3. Project Schedule | Project Schedule is developed; identification of activities is complete with sequencing of tasks for schedule development, development of schedule through identification of critical path/resources/duration | Sponsor approves methologies and schedule/resources; other department heads approve resources work involvement | Project Schedule Plan Network Diagram Bar Chart | Project Manager Project Team (4) Project Sponsor | 40 | 1 | 2.1
2.4. Project Budget | Project Budget is developed with estimated costs | Sponsor approves methologies and budget developed | Project Cost Management Plan Bottom Up Cost Estimating Project Budget Procurement Management Plan | Project Manager Project Team (4) Project Sponsor | 40 | 1 | 2.1
2.5. Project Documents & Templates | Development of additional documents and templates for assisting with development and monitoring of project | Documents and templates are developed and approved by majority of project team and project manager. | APWA Practices Checklist Cause and Effect Diagram Process Flow Diagram | Project Manager Project Team (4) | 20 | 1 | 2.1
2.6. Identify Risks & Risk Management Plan | Development of Risk Management Plan; complete a risk analysis identifying probablility and impact to project; complete a Risk Register that establishes root causes and possible responses; complete a SWOT analysis | Risks are identified, documented with possible responses and approved by majority of project team and project manager. | SWOT Analysis Risk Register Probability and Impact Matrix | Project Manager Project Team (4) | 40 | 2 | 2.1
2.7. Project Planning Gate with Steering Committee | PowerPoint presentation to Steering Committee for approval | Steering Committee gives the 'go ahead' for continuing project | Planning Gate PowerPoint Presentation | Project Manager Steering Committee (3) Project Sponsor | 24 | 2 | 2.1, 2.2, 2.3, 2.4, 2.5, 2.6
3. Project Kick-Off |  |  |  |  | 168 | 13
3.1. Internal Project Kick-Off | Project Manager and Project Team work together to develop meeting agenda and presentation | Agenda and PowerPoint is developed and approved by majority of project team and project manager. | Project Kick-Off Meeting Agenda and PowerPoint | Project Manager Project Team (4) | 55 | 3 | 2.7
3.1.1. Public Works Employees Kick-Off Meeting | Meeting to roll out the project to ME and Public Works employees | Meeting is concluded with all questions answered | Meeting Held | Project Manager Project Team (4) SME's (14) PW Employee (8)
3.1.2. Stakeholders Kick-Off Meeting | Meeting to roll out the project to stakeholders | Meeting is concluded with all questions answered | Meeting Held | Project Manager Project Team (4) Stakeholders (37)
3.2. Conduct Procurement | RFQ is developed and posted for consultant; bids are reviewed and scored; agreement is developed and signed | Agreement is signed by consultant and sponsor | RFQ for consultant/ Scoring Sheets Professional Services Agreeement | Project Manager Project Team (4) Finance Department (2) City Attorney Project Sponsor | 83 | 12 | 2.7
3.3. Submit Formal Application | Downloading, completing and submitting application for self-assessment with payment | Application and payment accepted | APWA Self-Assessment Application Purchase Requisition, P.O. and check |  | 10 | 1 | 3.1
3.3.1. Identify City Practices | Identification of APWA practices to be assessed and reported out to employees | Sponsor approves methologies and practices identified for self-assessment | APWA Final Checklist | Project Manager Project Team (5) Project Sponsor
3.4. Training by APWA for Project | Project Manager and Consultant attend APWA Workshop for training | Project Manager and Consultant attend training and come back prepared to train others | APWA Self-Assessment Software Manual | Project Manager Consultant | 20 | 1 | 3.2
4. Self-Assessment Execution |  |  |  |  | 6300 | 39
4.1. Data Collection | SMEs, PW employees and consultant begin to collect practices documentation for inputting into APWA self-assessment software program | Copies of policies, procedures and practices are uploading into a electronic holding file for verification of best practice | Electronic documents and files of practices | SMEs (14) PW Employees (24) | 5700 | 15 | 3.3, 3.4
4.1.1. Internal Collection | SMEs, PW employees and consultant begin to collect practices documentation for inputting into APWA self-assessment software program | Copies of policies, procedures and practices are uploading into a electronic holding file for verification of best practice | Electronic documents and files of practices | SMEs (14) PW Employees (24)
4.1.2. APWA On-Site Visit | APWA professional comes to city and reviews progress of work obtained; provides feedback and answers questions from Project Manager and Project Team | APWA professional onsite and provides pertinent feedback | Feedback | Project Manager Project Team (5) Project Sponsor
4.2. Gap Analysis | Consultant reviews, analyzes and verifies internal practices for gaps | All gaps are identified | Gap Checklist | Consultant | 360 | 18 | 4.1
4.2.1. Gap Recommendations | Consultant makes recommendations from gap analysis | All gaps are identified | Gap Analysis Report | Project Manager Project Team (5) Project Sponsor
4.2.2. Data & Process Development | SMEs, PW employees and consultant begin to develop gap practices with policies/procedures and develops documentation for inputting into APWA self-assessment software program | Consultant final report outlining Gaps | Electronic documents and files of practices | SMEs (14) PW Employees (24)
4.2.3. New Data & Process Approval by Sponsor | New policies, procedures and practices developed from the gap analysis is presented to sponsor for approval | Sponsor approves new practices, procedures and practices | Hard copies and electronic documents and files of practices | Project Manager Consultant Project Sponsor
4.3. Data Input in APWA Self-Assessment Software | All identified policies, procedures and practices are uploaded and inputted into APWA Self-Assessment Software | APWA Self-Assessment Software has all required policies, procedures and practices uploaded | APWA Self-Assessment Software Report | Project Manager Project Team (5) PW Employees (2) | 240 | 6 | 4.1, 4.2
5. Monitor Self-Assessment |  |  |  |  | 320 | 58
5.1. Maintain Project Management Plan | Control and monitor Project, Integration, Stakeholders, Communications, Risk and Change Management Plans | Project, Integration, Stakeholders, Communications, Risk and Change Management Plans are up up-to-date with the latest information and never more than five business days out of date | Project Management Plan updated Integration Management Plan updated Stakeholder Management Plan updated Comm. Management Plan updated Risk Management Plan updated Change Management Plan updated | Project Manager Project Team (5) | 15 | 52 | 2.7, 4.1, 4.2, 4.3
5.2. Manage Scope, Schedule, Budget | Control and monitor Scope, Schedule and Budget Management Plans | Scope, Schedule and Buget Management Plans are up up-to-date with the latest information and never more than five business days out of date | Scope Management Plan updated Schedule Management Plan updated Budget Management Plan updated | Project Manager Project Team (5) | 60 | 52 | 2.7, 4.1, 4.2, 4.3
5.2.1. Project Status Reports | Hold monthly status meeting with sponsor | Sponsor approves status | Project Status Report | Project Manager Project Sponsor
5.2.2. Evaluate/Address Risks | Hold weeklymeetings with team to evaluate and address any risks | Risks identified and responded to | Risk Register updated | Project Manager Project Team (5)
5.3. Manage Procurement | Control and monitor procurement of consultant and work performanance and quality | Consultant report card is at standard or above | Consultant Report Card | Project Manager Consultant | 40 | 40 | 3.2
5.3.1. Manage Invoices | Review and process invoices for payment to consultant | Payment of invoice | Invoices Payment Checks
5.3.2. Verify Quality & Deliverables | Control and monitor procurement of consultant and work performanance and quality | Consultant report card is at standard or above | Consultant Report Card | Project Manager Consultant
5.4. Manage Resources | Control and monitor Human Resources Management Plan | Human Resources Management Plan is up up-to-date with the latest information and never more than five business days out of date | Human Resources Plan updated | Project Manager Project Team (5) | 70 | 52 | 2.7, 4.1, 4.2, 4.3
5.4.1. Project Meetings | Hold monthly project meeting with Project Team | Project updates and issues are given or identified and addressed | Project Update Report Change Control Report | Project Manager Project Team (5)
5.4.2. Stakeholder Meetings | Hold update meeting after gate meetings with stakeholders to keep them updated on project progress | Project updates are given and concerns are identified and documented for possible risk and future reporting out | Project Update Report Change Control Report | Project Manager Stakeholders (37)
5.5. Manage Quality |  |  |  |  | 121 | 52 | 2.7, 4.1, 4.2, 4.3
5.5.1. Complete Check Sheets | Monthly review of APWA Checklist is reviewed for progress of project and scheduling risks | Project schedule is on-time | Risk Register updated | Project Manager Project Team (5)
5.5.2. Data Quality Meetings | Hold monthly meeting with Project Team for input on quality control of policies, procedures and practices reviewed for best practices | Project quality and issues are identified and documented for additional work | Quality Management Report Change Control Report | Project Manager Project Team (5)
5.5.3. Validate Data | Weekly review of electronic documents and files are done to ensure best practice and completeness are verified | Electronic documents are moved into final phase | Electronic documents and files of practices in final folder | Project Manager Project Team (5)
5.6. Readiness Meeting with Sponsor | Meeting with sponsor to verify data on APWA Self-Assessment software report in order to begin close-out of project | Meeting with sponsor is held | APWA Self-Assessment software report | Project Manager Project Sponsor | 4 | 2 | 4.3, 5.1, 5.2, 5.3, 5.4, 5.5
5.6.1. Internal Readiness Check | Review of APWA practices checklist | All APWA practices on checklist are complete | APWA Practices Checklist | Project Manager Project Sponsor
5.6.2. Prep Data & Presentation | Uploading of APWA Self-Assessment software report with final status report done for presentation to Project Sponsor | APWA Self-Assessment softwareand status reports are accepted by Project Sponsor | APWA Self-Assessment software report Status Report | Project Manager Project Sponsor
5.7. Steering Committee Meeting | PowerPoint presentation to Steering Committee for approval | Steering Committee gives the 'go ahead' for continuing project | Initiation Gate PowerPoint Presentation | Project Manager Steering Committee (3) Project Sponsor | 10 | 2 | 5.6
6. Close-Out Self-Assessment |  |  |  |  | 102 | 12
6.1. Council Meeting | Date for Council meeting is identified and confirmed for APWA Self-Assessment Project Agenda Bill Presentation | City Council Receives Report | APWA PowerPoint Presentation | Project Manager Project Sponsor | 40 | 6 | 5.7
6.2.1. Prep Agenda Bill | Agenda Bill is developed and routed for signatures and placed on Council Agenda | Agenda Bill placed on Council Meeting | Agenda Bill APWA PowerPoint Presentation | Project Manager Project Sponsor City Manager City Clerk City Attorney Finance Director Planning Director
6.2.2. Public Notice | Public Notice is sent out by City Clerk giving notice of project being placed on agenda | Public Notice of Agenda Item | Public Notice | City Clerk
6.2.3. Prep Presentation | Agenda Bill PowerPoint presentation is developed and routed to Project Sponsor for final approval | Agenda Bill presentation placed in Council Meeting packet | APWA PowerPoint Presentation | Project Manager Project Sponsor City Clerk
6.2. Steering Committee Meeting | PowerPoint presentation to Steering Committee for approval | Steering Committee gives the 'go ahead' for continuing project | Close-Out Gate PowerPoint Presentation | Project Manager Steering Committee (3) Project Sponsor | 20 | 2 | 6.1
6.3. Establish Accreditation Project | Review accreditation requirements for APWA Accrediation in order to begin the accreditation process | Business Case is developed | Business Case | Project Manager | 12 | 1 | 6.1
6.3.1. Business Case | Project Manager develops business case to present to sponsor for approval to start accrediation project planning | Business Plan is signed of by sponsor for proceeding with project planning | Project description and desired outcome | Project Manager Project Sponsor
6.3.2. Project Charter | Project Manager establishes project team and works together to develop project charter for presentation to steering committee to begin planning project | Project Charter is signed off by sponsor | Project Charter Draft Signed | Project Manager Project Team (5) Project Sponsor
6.4. Internal Project Close-Out | Develop close-out celebrations, archive data, make final payments and close-out P.O., develop stakeholder's close-out meeting agenda | Close-Out Party is planned and confirmed, invitations sent, Stakeholder agenda is developed, P.O. is closed and all invoices paid and database of self-assessment is archived. | Close-Out Party Invitation, site, date, etc. Stakeholder Meeting Agenda Final Checks Database File Folder with Project Documentation | Project Manager Project Team (5) | 30 | 6 | 6.1
6.4.1. Project Team Party | PARTY!!!! | Party held | Thank you speech | Project Manager Project Team (5)
6.4.2. Stakeholder Meeting | Meeting to close out the project is held | Meeting is concluded with all questions answered | Meeting Held | Project Manager Project Team (4) Stakeholders (37)

## APWA Critical Path (hidden)
APWA Self-Assessment: Network Diagram
Project Start: Feb. 19, 2015
[20 empty] | 2.2 |  |  | 1
Scope
[20 empty] | ES | EF | LS | LF
[20 empty] | 6 | 7 | 7 | 8
Total Slack = 1
Free Slack = 1
[20 empty] | 2.3 |  |  | 1 | [5 empty] | 3.1 |  |  | 3 | 3.3 |  |  |  | 1
[20 empty] | Schedule | [8 empty] | Kick-Off |  |  |  | Application
[20 empty] | ES | EF | LS | LF | [5 empty] | ES | EF | LS | LF | ES | EF |  | LS | LF
[20 empty] | 6 | 7 | 7 | 8 | [5 empty] | 10 | 13 | 19 | 22 | 13 | 14 |  | 22 | 23
[20 empty] | Total Slack = 1 | [8 empty] | Total Slack = 9 |  |  |  | Total Slack = 9
[20 empty] | Free Slack = 1 | [8 empty] | Free Slack = 9 |  |  |  | Free Slack = 9
Start |  |  | 0 | 1.1 |  |  | 1 | 1.2 |  |  | 1 | 1.3 |  |  | 2 | 2.1 |  |  | 2 | 2.4 |  |  | 1 | 2.7 |  |  | 2 | [11 empty] | 4.1 |  |  | 15 |  | 4.2 |  |  | 18
Start Task |  |  |  | Business Case |  |  |  | Project Charter |  |  |  | Gate Meeting |  |  |  | Mgnt Plan |  |  |  | Budget |  |  |  | Gate Meeting | [14 empty] | Data Collection |  |  |  |  | Gap Analysis
ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | [11 empty] | ES | EF | LS | LF |  | ES | EF | LS | LF
0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 1 | 2 | 2 | 4 | 2 | 4 | 4 | 6 | 4 | 6 | 6 | 7 | 7 | 8 | 8 | 10 | 8 | 10 | [11 empty] | 23 | 38 | 23 | 38 |  | 38 | 56 | 38 | 56
|  |  |  | Total Slack = 0 |  |  |  | Total Slack = 0 |  |  |  | Total Slack = 0 |  |  |  | Total Slack = 0 |  |  |  | Total Slack = 1 |  |  |  | Total Slack = 0 | [14 empty] | Total Slack = 0 |  |  |  |  | Total Slack = 0
|  |  |  | Free Slack = 0 |  |  |  | Free Slack = 0 |  |  |  | Free Slack = 0 |  |  |  | Free Slack = 0 |  |  |  | Free Slack = 1 |  |  |  | Free Slack = 0 | [14 empty] | Free Slack = 0 |  |  |  |  | Free Slack = 0
[29 empty] | 3.2 |  |  | 12 | 3.4 |  |  |  | 1
[20 empty] | 2.5 |  |  | 1 | [5 empty] | Procurement |  |  |  | Training | [26 empty] | 6.2 |  |  | 2
[20 empty] | Doc & Templates | [8 empty] | ES | EF | LS | LF | ES | EF |  | LS | LF |  |  |  | 4.3 |  |  | 6 | [15 empty] | Gate Meeting
[20 empty] | ES | EF | LS | LF | [5 empty] | 10 | 22 | 10 | 22 | 22 | 23 |  | 22 | 23 |  |  |  | Data Iinputting | [18 empty] | ES | EF | LS | LF
[20 empty] | 6 | 7 | 7 | 8 | [17 empty] | ES | EF | LS | LF | [15 empty] | 72 | 73 | 77 | 78
[29 empty] | Total Slack = 0 |  |  |  | Total Slack = 0 | [7 empty] | 56 | 62 | 56 | 62
[20 empty] | Total Slack = 1 | [8 empty] | Free Slack = 0 |  |  |  | Free Slack = 0 | [26 empty] | Total Slack = 5
[20 empty] | Free Slack = 1 | [20 empty] | Total Slack = 0 | [18 empty] | Free Slack = 5
Free Slack = 0
[20 empty] | 2.6 |  |  | 2 |  |  |  | 5.1 |  |  | 52 | [17 empty] | 5.6 |  |  | 2 | 5.7 |  |  | 2 | 6.1 |  |  | 6 | 6.3 |  |  | 1 | FINISH
[20 empty] | Risks | [6 empty] | Monitor Mgnt Plan | [20 empty] | Readiness Meeting |  |  |  | Gate Meeting |  |  |  | Council Meeting |  |  |  | Accreditation |  |  |  | PROJECT CLOSED
[20 empty] | ES | EF | LS | LF |  |  |  | ES | EF | LS | LF | [17 empty] | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF | ES | EF | LS | LF
[20 empty] | 6 | 8 | 6 | 8 |  |  |  | 10 | 62 | 10 | 62 | [17 empty] | 62 | 64 | 62 | 64 | 64 | 66 | 64 | 66 | 66 | 72 | 66 | 72 | 72 | 73 | 77 | 78 | 78 | 78 | 78 | 78
[20 empty] | Total Slack = 0 | [6 empty] | Total Slack = 0 | [20 empty] | Total Slack = 0 |  |  |  | Total Slack = 0 |  |  |  | Total Slack = 0 |  |  |  | Total Slack = 5
[20 empty] | Free Slack = 0 | [6 empty] | Free Slack = 0 | [20 empty] | Free Slack = 0 |  |  |  | Free Slack = 0 |  |  |  | Free Slack = 0 |  |  |  | Free Slack = 5
[27 empty] | 5.2 |  |  | 52 | [29 empty] | 6.4 |  |  | 6
[27 empty] | Monitor S, S, B | [32 empty] | Close-Out
[27 empty] | ES | EF | LS | LF | [29 empty] | ES | EF | LS | LF
[27 empty] | 10 | 62 | 10 | 62 | [29 empty] | 72 | 78 | 72 | 78
[27 empty] | Total Slack = 0 | [32 empty] | Total Slack = 0
[27 empty] | Free Slack = 0 | [32 empty] | Free Slack = 0
[34 empty] | 5.3 |  |  |  | 40
Monitor Procurement
[34 empty] | ES | EF |  | LS | LF
[34 empty] | 22 | 62 |  | 22 | 62
Total Slack = 0
Free Slack = 0
[27 empty] | 5.4 |  |  | 52
Monitor Resources
[27 empty] | ES | EF | LS | LF
[27 empty] | 10 | 62 | 10 | 62
Total Slack = 0
Free Slack = 0
[27 empty] | 5.5 |  |  | 52
Monitor Quality
[27 empty] | ES | EF | LS | LF
[27 empty] | 10 | 62 | 10 | 62
Total Slack = 0
Free Slack = 0
Critical Path = 33