## WBS
APWA Self-Assessment
1.0 Initiate | 2.0 Plan |  | 3.0 Project Kick-Off |  |  | 4.0 Self-Assessment Execution |  |  |  | 5.0 Monitor Self-Assessment |  |  |  |  | 6.0 Close-Out Self-Assessment
1.1 Establish Business Case | 2.1 Project Management Plan & Subsidiary Plans |  | 3.1 Internal Project Kick-Off |  |  | 4.1 Identify City Practices |  |  |  | 5.1 Maintain Project Management Plan |  |  |  |  | 6.1 Steering Committee Meeting
1.2 Project Charter | 2.2 Project Scope | 3.1.1 Project Team Kick-Off Meeting |  | 3.1.2 Stakeholders Kick-Off Meeting |  | 4.2 Data Collection |  |  |  | 5.2 Manage Scope, Schedule, Budget |  |  |  |  | 6.2 Council Meeting
1.3 Initiation Gate with Steering Committee | 2.3 Project Schedule |  | 3.2 Conduct Procurement |  | 4.2.1 Internal Collection |  | 4.2.2 APWA On-Site Visit |  | 5.2.1 Project Status Reports |  | 5.2.2 Evaluate/Address Risks |  | 6.2.1 Prep Agenda Bill |  | 6.2.2 Public Notice |  | 6.2.3 Prep Presentation
| 2.4 Project Budget |  | 3.3 Submit Formal Application |  |  | 4.3 Gap Analysis |  |  |  | 5.3 Manage Procurement |  |  |  |  | 6.3 Establish Accreditation Project
| 2.5 Project Documents & Templates |  | 3.4 Training by APWA for Project |  |  | 4.3.1 Gap Recommendations |  |  | 5.3.1 Manage Invoices |  | 5.3.2 Verify Quality & Deliverables |  |  | 6.3.1 Business Case |  | 6.3.2 Project Charter
| 2.6 Identify Risks & Risk Management Plan |  |  |  |  | 4.3.2 Data & Process Development |  |  |  | 5.4 Manage Resources |  |  |  |  | 6.4 Internal Project Close-Out
| 2.7 Project Planning Gate with Steering Committee |  |  |  |  | 4.3.3 New Data & Process Approval by Sponsor |  |  | 5.4.1 Project Meetings |  | 5.4.2 Stakeholder Meetings |  |  | 6.4.1 Project Team Party |  | 6.4.2 Stakeholder Meeting
[6 empty] | 4.4 Peer Review and Report |  |  |  | 5.5 Manage Quality
Closed
[6 empty] | 4.5 Data Input in APWA Self-Assessment Software |  | 5.5.1 Complete Check Sheets |  | 5.5.2 Data Quality Meetings |  | 5.5.3 Validate Data
5.6 Readiness Meeting with Sponsor
[8 empty] | 5.6.1 Internal Readiness Check |  | 5.6.2 Peer Review |  | 5.6.3 Prep Data & Presentation
5.7 Steering Committee Meeting