## Risk Register
| Project: APWA Self-Assessment |  | NOTE: Select "Show all Comments" from the toolbar to see my notes |  |  |  | KEY:
Key/ Critical
Intermediate
Minor
RISK IDENTIFICATION & MITIGATION | [9 empty] | ACTION PLAN
Ref | Category | Risk | Potential Impact | Completed Mitigation Action (to date) | Probability | Impact | Risk Score/ Category | Cost Impact (Project Costs) | Schedule Impact [weeks] | Action Plan | Responsible | Next Action Target Date | Date Achieved | COMMENTS
1 | External | Public does not approve staff's submittal at Council Meeting | Could delay entire accreditation process; could result in expanded scope as directed by Council (add new services) |  |  |  | 0
2 | Internal | City Council delays approval to submit self-assessment | Self-assessment project delayed as is overall accreditation process |  |  |  | 0
1 | Internal | Steering Committee does not sign off on pursuing rest of ActiveNet training Process | Department does not achieve long term objective of accreditation in ActiveNet |  | 5 | 4 | 20
2 | Internal | ActiveNet System changes and related training is no longer an organizational priority | Invested resources to pursue the project are wasted; costs of trainging tools are lost; organization does not gain credibility through accreditation in ActiveNet System |  | 3 | 3 | 9
3 | Internal | City leadership changes meeting date due to scheduling conflicts with other agenda items | Self-assessment project delayed as is overall accreditation process |  | 2 | 3 | 6
4 | Internal | Inaccurate assumptions during the planning phase | Agreed strategies and plans in scope of work requires additional review and amendment; cost and time implications |  | 2 | 4 | 8
5 | Internal | Employees who are being trained will not read or fully understand the contents of the kick-off email | Employees will not understand the importance of the training process and fully support the effort |  | 3 | 2 | 6
6 | Internal | Stakeholders are unable to attend the Stakeholder Kickoff Meeting | Stakeholders will not understand the importance of the self-assessment process and fully support the effort |  | 3 | 2 | 6
7 | Internal | Employees do not fully support the training process | The process will be much more difficult, signficantly more challenging and will take longer to accomplish. Staff may also not retain any information the modules sought to teach. |  | 3 | 2 | 6
8 | Client | Training services are ineffective | An plan for training personnel is not developed; documentation preparation is ineffective |  | 1 | 2 | 2
9 | Internal | Data received from the projec team is incomplete or is substandard | The project team would have to redo work which would impact the project schedule. |  | 2 | 4 | 8
10 | Internal | Another higher priority project takes away available resources | The project would be delayed until resources become available, the result impacts the overall project schedule. |  | 5 | 4 | 20
11 | External | Module within LITMOS develops a bug found during QA/QC and data needs to be re-entered | This would impact available resources, project schedule, and project cost. |  | 2 | 3 | 6
12 | External | Project Team member delivers data ahead of time and under budget | This would result in extra cushion in both the project budget and schedule |  | 1 | 3 | 3
13 | Internal | Sign-off by steering committee leads to additional work requirements | Possible redesign and additional requirements are added to project creating delays in kick-off. |  | 1 | 4 | 4
14 | Internal | Sponsor elects to reduce the number of exams in each chapter to be included in self-assessment | Possible reduction in schedule due to less exams being submitted |  | 2 | 5 | 10
15 | Internal | Inaccurate assumptions during the planning phase | Assumptions in estimating resources, schedule, budget, stakeholders and/or communication haven't been fully identified creating changes to several plans |  | 2 | 5 | 10
16 | Organizational | Resource conflicts with other projects | Not enough resources are available or outside departments don't provide the resources necessary to stay within schedule |  | 4 | 4 | 16
17 | Organizational | Approval and decision processes cause delays | Sponsor and/or Steering Committee aren't available for meetings that are scheduled for approvals causing delays |  | 4 | 5 | 20
18 | Internal | Electronic holding file compromised; files accidentally erased or corrupted and not recoverable | Significant rework and addition of time |  | 2 | 5 | 10
19 | Internal | Consultant identified none or very few gaps in data | Collapse in schedule |  | 2 | 1 | 2
20 | Internal | Consultant identifies significant gaps that cannot be addressed within the project schedule | Staff may need to reevaluate practices for submittal. Project team will need to execute contingency plans |  | 3 | 3 | 9
21 | External | LITMOS online system becomes unstable/unreliable | Delays in uploading data. May define/limit which users will have the ability to upload data to the system. |  | 3 | 2 | 6
22 | Internal | New policies/procedures take too long to develop, or team is unable to gain consensus on new policies/procedures | Adds time to schedule. |  | 3 | 2 | 6
23 | External | Staff may not be able to complete required materials during time frame necessary | Re-evaluate schedule. |  | 2 | 2 | 4
24 | Internal | Data not available in electronic format | Additional resources needed to digitize data, will add time to schedule |  | 4 | 2 | 8
Note on D2: Justin Goulet: @Bonnie, Are we creating an accreditation in accordance with the training modules? I see the accreditation as being able to access the system, but I am not sure exactly how much control we have over access
Note on F10: Justin Goulet: Scores may need to be re-evaluated. I took the scores from the previous. Note, even though the scores were from the previous Risk Register, each item was read and adjusted to fit the scope of our project.

## Scoring Matrix
Risk Scoring Matrix | [7 empty] | Probability Categories
Impact | Very High/ Critical | 5 |  | 4 |  | 2 |  | Description |  | Prob | Scale Value
| High/ Critical | 4 | 1 | 3 |  | 1 | 2 | VH | Imminent | > 95% | 5
| Medium/ Serious | 3 | 1 | 3 | 3 | 1 |  | H | Probable | 71-94% | 4
| Low/ Marginal | 2 | 1 | 1 | 5 | 1 |  | M | Could happen | 30-70% | 3
| Very Low/ Marginal | 1 |  | 1 |  |  |  | L | Improbable | 5-29% | 2
|  |  | 1 | 2 | 3 | 4 | 5 | VL | Highly unlikely | <5% | 1
|  |  | Very Low/ Improbable | Low/ Improbable | Medium/ Could happen | High/ Probable | Very High/ Probable | Impact Categories
[8 empty] | Description |  | Guide Scenario |  | Scale Value
[8 empty] | VH | Critical | Failure that involves significant rework, modification or reassessment |  | 5
[8 empty] | H | Critical | Failure that involves significant rework, modification or reassessment |  | 4
[8 empty] | M | Serious | Failure or setback that causes additional work and reassessment but containable |  | 3
[8 empty] | L | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 2
|  |  | Probability |  |  |  |  | VL | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 1
Risk Category & Action
Key/ Critical Risks - closely monitor, manage & develop fallback plans
Intermediate Risks - monitor and manage to mitigate/ include specific risk allowances in cost estimate & schedule
Minor Risks - general allowance in base cost estimate & schedule