## Risk Register
| Project: APWA Self-Assessment |  | NOTE: Select "Show all Comments" from the toolbar to see my notes |  |  |  | KEY:
Key/ Critical
Intermediate
Minor
RISK IDENTIFICATION & MITIGATION | [9 empty] | ACTION PLAN
Ref | Category | Risk | Potential Impact | Completed Mitigation Action (to date) | Probability | Impact | Risk Score/ Category | Cost Impact (Project Costs) | Schedule Impact [weeks] | Action Plan | Responsible | Next Action Target Date | Date Achieved | COMMENTS
1 | External | Public does not approve staff's submittal at Council Meeting | Could delay entire accreditation process; could result in expanded scope as directed by Council (add new services) |  |  |  | 0
2 | Internal | City Council delays approval to submit self-assessment | Self-assessment project delayed as is overall accreditation process |  |  |  | 0
1 | Internal | Steering Committee does not sign off on pursuing rest of ActiveNet training Process | Department does not achieve long term objective of accreditation in ActiveNet |  | 5 | 4 | 20
2 | Internal | ActiveNet System is replaced and related training is no longer an organizational priority to make way for new system training | Invested resources to pursue the project are used up; costs of trainging tools are lost, or minimal materials may be transferred to new system; organization does not gain credibility through related resources. |  | 3 | 3 | 9
3 | Internal | City leadership changes meeting date due to scheduling conflicts with other agenda items | Self-assessment project delayed as is overall n training process |  | 2 | 3 | 6
4 | Internal | Inaccurate assumptions during the planning phase | Agreed strategies and plans in scope of work requires additional review and amendment; cost and time implications |  | 2 | 4 | 8
5 | Internal | Employees who are being trained will not read or fully understand the contents of the kick-off email | Employees will not understand the importance of the training process and fully support the effort. Could hinder the efficiency of employees by not allowing them to work until trained. |  | 3 | 2 | 6
6 | Internal | Stakeholders are unable to attend the Stakeholder Kickoff Meeting | Stakeholders will not understand the importance of the self-assessment process and fully support the effort |  | 3 | 2 | 6
7 | Internal | Employees do not fully support the training process | The process will be much more difficult, signficantly more challenging and will take longer to accomplish. Staff may also not retain any information the modules sought to teach. |  | 3 | 2 | 6
8 | Client | Training services are ineffective | An plan for training personnel is not developed; documentation preparation is ineffective |  | 1 | 2 | 2
9 | Internal | Data received from the project team is incomplete or is substandard | The project team would have to redo work which would impact the project schedule. |  | 2 | 4 | 8
10 | Internal | Another higher priority project takes away available resources | The project would be delayed until resources become available, the result impacts the overall project schedule. |  | 5 | 4 | 20
11 | External | Module within LITMOS develops a bug found during QA/QC and data needs to be re-entered | This would impact available resources, project schedule, and project cost. |  | 2 | 3 | 6
12 | External | Project Team member delivers data ahead of time and under budget | This would result in extra cushion in both the project budget and schedule |  | 1 | 3 | 3
13 | Internal | Sign-off by steering committee leads to additional work requirements | Possible redesign and additional requirements are added to project creating delays in kick-off. |  | 1 | 4 | 4
14 | Internal | Sponsor elects to reduce the number of exams in each chapter to be included in self-assessment | Possible reduction in schedule due to less exams being submitted |  | 2 | 5 | 10
15 | Internal | Inaccurate assumptions during the planning phase | Assumptions in estimating resources, schedule, budget, stakeholders and/or communication haven't been fully identified creating changes to several plans |  | 2 | 5 | 10
16 | Organizational | Resource conflicts with other projects | Not enough resources are available or outside departments don't provide the resources necessary to stay within schedule |  | 4 | 4 | 16
17 | Organizational | Approval and decision processes cause delays | Sponsor and/or Steering Committee aren't available for meetings that are scheduled for approvals causing delays |  | 4 | 5 | 20
18 | Internal | Electronic holding file compromised; files accidentally erased or corrupted and not recoverable | Significant rework and addition of time |  | 2 | 5 | 10
19 | Internal | Consultant identified none or very few gaps in data | Collapse in schedule |  | 2 | 1 | 2
20 | Internal | Consultant identifies significant gaps that cannot be addressed within the project schedule | Staff may need to reevaluate practices for submittal. Project team will need to execute contingency plans |  | 3 | 3 | 9
21 | External | LITMOS online system becomes unstable/unreliable | Delays in uploading data. May define/limit which users will have the ability to upload data to the system. |  | 3 | 2 | 6
22 | Internal | New policies/procedures take too long to develop, or team is unable to gain consensus on new policies/procedures | Adds time to schedule. |  | 3 | 2 | 6
23 | External | Staff may not be able to complete required materials during time frame necessary | Re-evaluate schedule. |  | 2 | 2 | 4
24 | Internal | Data not available in electronic format | Additional resources needed to digitize data, will add time to schedule |  | 4 | 2 | 8
25 | Internal | Documents become corrupt while editing | Documents will have to be re-created/corrected to correspond with data lost. |  | 2 | 5 | 10
26 | Internal | User may have unauthorized permissions to documents previously edited | Document Permissions must be reassigned in respondance to related material |  | 1 | 2 | 2
27 | Internal | ActiveNet System Updates and modules may become absolete | All affected courses/modules will need to be reevaulated. Changes must be constant and related to the infromation the stakeholders have at their disposal. Stakeholders may become frustrated with inconsistancy |  | 5 | 5 | 25
Note on D2: Justin Goulet: @Bonnie, Are we creating an accreditation in accordance with the training modules? I see the accreditation as being able to access the system, but I am not sure exactly how much control we have over access
Note on D10: Bonnie Elliott: Really long term objective to decrease the amount of time between person being hired and actually being able to work fully in system; also, reduce trainer time with basic training.
Note on F10: Justin Goulet: Scores may need to be re-evaluated. I took the scores from the previous. Note, even though the scores were from the previous Risk Register, each item was read and adjusted to fit the scope of our project.
Note on C11: Bonnie Elliott: I think it may be more keeping up with all the changes; modifying/updating our training materials
Note on D11: Bonnie Elliott: More like training is outdated causing some errors or frustration for staff; increase training time for trainers
Note on D14: Bonnie Elliott: Could prolong the time between their being hired and actually able to do their work
Note on C25: Bonnie Elliott: Could also have an issue with hours; many front line staff are PT so have limited hours that supervisor may not approve their work/assistance with project

## Scoring Matrix
Risk Scoring Matrix | [7 empty] | Probability Categories
Impact | Very High/ Critical | 5 |  | 4 |  | 2 |  | Description |  | Prob | Scale Value
| High/ Critical | 4 | 1 | 3 |  | 1 | 2 | VH | Imminent | > 95% | 5
| Medium/ Serious | 3 | 1 | 3 | 3 | 1 |  | H | Probable | 71-94% | 4
| Low/ Marginal | 2 | 1 | 1 | 5 | 1 |  | M | Could happen | 30-70% | 3
| Very Low/ Marginal | 1 |  | 1 |  |  |  | L | Improbable | 5-29% | 2
|  |  | 1 | 2 | 3 | 4 | 5 | VL | Highly unlikely | <5% | 1
|  |  | Very Low/ Improbable | Low/ Improbable | Medium/ Could happen | High/ Probable | Very High/ Probable | Impact Categories
[8 empty] | Description |  | Guide Scenario |  | Scale Value
[8 empty] | VH | Critical | Failure that involves significant rework, modification or reassessment |  | 5
[8 empty] | H | Critical | Failure that involves significant rework, modification or reassessment |  | 4
[8 empty] | M | Serious | Failure or setback that causes additional work and reassessment but containable |  | 3
[8 empty] | L | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 2
|  |  | Probability |  |  |  |  | VL | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 1
Risk Category & Action
Key/ Critical Risks - closely monitor, manage & develop fallback plans
Intermediate Risks - monitor and manage to mitigate/ include specific risk allowances in cost estimate & schedule
Minor Risks - general allowance in base cost estimate & schedule